## Sheet1
Cumulative Totals for CFD
To Do values remain as they are.
In Progress values should be cumulative with To Do (e.g., In Progress + To Do).
Done values should be cumulative with In Progress and To Do.
| Date | To Do | In Progress | Done
| Week 1 | 5 | 0 | 0
| Week 2 | 3 | 1 | 1
| Week 3 | 2 | 2 | 1
| Week 4 | 1 | 1 | 3
| Week 5 | 0 | 0 | 5
2. Burndown Chart Data
The Burndown Chart shows how much work (in terms of tasks or story points) remains over time.
| Week | Ideal Remaining Milestones | Actual Remaining Milestones
| Week 1 | 5 | 5
| Week 2 | 4 | 4
| Week 3 | 3 | 3
| Week 4 | 2 | 2
| Week 5 | 0 | 0
Ideal Remaining Tasks represents the target line if work is completed evenly over time.
Actual Remaining Tasks shows the real progress of work completed.
X-axis showing dates and the Y-axis showing the remaining tasks.
3. Burnup Chart Data
The Burnup Chart shows cumulative work completed over time, indicating progress toward the total goal.
| Week | Total Milestones (Scope) | Milestones Completed
| Week 1 | 5 | 0
| Week 2 | 5 | 1
| Week 3 | 5 | 2
| Week 4 | 5 | 3
| Week 5 | 5 | 5
Total Scope remains constant at 30, representing the total number of t