## Sheet2
User Story | Round 1 - Fibonacci Estimates |  |  |  | Discussion notes | Round 2 - Fibonacci Estimates |  |  |  | Discussion Notes | Final Decision
Varsha | Hemanth | Girish | Wen |  |  | Varsha | Hemanth | Girish | Wen
3. Work Experience Detailing | 3 | 5 | 5 | 3 | Team considered this task a medium effort since the user already has work experience data, and it's mainly about organizing and summarizing key achievements. | 5 | 5 | 8 | 5 | After discussing the need for detailed descriptions, ensuring consistency in tone across different roles, and including measurable achievements, the team realized it required more effort than anticipated. | The final decision was that this task involved more effort due to the need to effectively communicate achievements across multiple roles and ensure consistency throughout the profile. The team increased the Fibonacci score to reflect the additional work needed.
4. Adding Relevant Skills | 2 | 3 | 3 | 2 | The team viewed this as a simple task, mainly requiring the addition of known skills to the profile. | 3 | 5 | 5 | 3 | Revised Estimate: After considering the importance of selecting the right skills, keyword optimization, and the impact of prioritizing certain skills over others, the team decided the effort was slightly higher. | Final decision recognized that the task requires strategic selection of skills and keyword optimization to align with recruiters’ searches, so the final effort estimate increased slightly compared to Round 1.
5. Seeking Skill Endorsements | 2 | 2 | 3 | 2 | Initial Estimate: The team initially considered this task straightforward, as it involved sending endorsement requests to colleagues and supervisors. | 3 | 5 | 5 | 3 | Revised Estimate: Upon further reflection, the team recognized that this task may require multiple rounds of requests and follow-ups, as well as selecting the right people for endorsements. | After realizing that the effort required more coordination and follow-ups than initially expected, the team increased the effort score for this task.
6. Thought Leadership Post | 3 | 5 | 8 | 5 | Initial Estimate: The team estimated this task as moderately challenging since it involves drafting, revising, and publishing an article on LinkedIn. | 5 | 8 | 8 | 8 | Revised Estimate: After discussing the need for thorough research, ensuring that the post is engaging and well-structured, and optimizing it for maximum visibility, the team decided it involved significant effort. | Final decision recognized that significant effort is needed to write a well-researched, engaging, and optimized article, so the estimate was further increased.
7. Profile Multimedia Enhancements | 2 | 3 | 5 | 3 | Initial Estimate: The team initially considered this a relatively simple task, mainly involving uploading multimedia content to the profile. | 5 | 5 | 5 | 5 | Upon further reflection, the team realized that ensuring the multimedia elements are high quality, relevant, and well-integrated into the profile required more strategic thought and effort. | The effort was increased slightly after recognizing the importance of high-quality multimedia integration and relevance to the profile's purpose.
8. Professional Networking | 3 | 2 | 3 | 2 | The team initially considered this a straightforward task, focusing on sending connection requests. | 5 | 5 | 5 | 5 | Revised Estimate: After considering the importance of targeting the right professionals and the need for personalization in connection requests, the team recognized that this could take more effort. | Personalizing connection requests and targeting the right professionals led to an increased effort estimate for networking on LinkedIn.
9. Industry Group Participation | 2 | 2 | 3 | 2 | Initial Estimate: The team estimated this as a simple task of joining groups | 5 | 5 | 5 | 5 | Revised Estimate: After realizing that the task also involves finding the most active and relevant groups, engaging in discussions, and making contributions, the effort was reassessed. | Final decision concluded that the effort to effectively participate in industry groups required ongoing engagement and contribution, leading to a higher effort estimate than initially expected.
10. Updating Certifications Section | 2 | 3 | 3 | 3 | Initial Estimate: The team viewed this as a simple task of adding certifications | 3 | 5 | 5 | 5 | Revised Estimate: The team later recognized that selecting the most relevant certifications and formatting them correctly to highlight their importance might take more effort. | The team increased the effort score after recognizing the importance of formatting and highlighting certifications correctly to showcase their relevance.
11. Track Profile Engagement | 2 | 3 | 2 | 2 | The team initially viewed this as a straightforward task, mainly involving checking LinkedIn's analytics features. | 3 | 5 | 5 | 3 | After considering that adjustments to the profile based on data would be necessary, the team increased the effort score. | The task of monitoring engagement and adjusting the profile accordingly led to a revised effort estimate, reflecting ongoing adjustments and analytics interpretation.
12. Personalized Connection Requests | 3 | 3 | 5 | 3 | The team initially viewed this as a moderate task, primarily focused on sending out personalized connection requests | 5 | 8 | 5 | 5 | Revised Estimate: After recognizing the importance of tailoring each request for maximum impact, the team increased the effort score. | Customizing each connection request for maximum impact raised the task's effort significantly, especially as personalized messages were key to building relationships.