## Sheet1
User Story | Round 1 Fibonacci Estimates |  |  |  | Discussion notes | Round 2 - Fibonacci Estimates |  |  |  | Discussion Notes | Final Decision
Varsha | Hemanth | Girish | Wen |  |  | Varsha | Hemanth | Girish | Wen
2. Summary section Improvement - To refine LinkedIn profile summary, so that it highlights skills, experience, and aspirations in a professional and engaging manner | 5 | 5 | 3 | 3 | Varsha: This task seems like a good opportunity to showcase our skills and experiences effectively. | 5 | 8 | 5 | 5 | Varsha: Detailed descriptions are necessary for clarity. | The final decision was that this task involved more effort due to the need to effectively communicate achievements across multiple roles and ensure consistency throughout the profile. The team increased the Fibonacci score to reflect the additional work needed.
[5 empty] | Hemanth: We have to ensure clarity and consistency. |  |  |  |  | Hemanth: We need consistency across different roles.
[5 empty] | Girish: Let's focus on measurable achievements. |  |  |  |  | Girish: Including measurable achievements adds value.
[5 empty] | Wen: Organizing key points will be crucial. |  |  |  |  | Wen: It’s more work than I initially thought.
3. Adding Relevant Skills | 3 | 3 | 2 | 2 | Varsha: Adding known skills should be straightforward. | 5 | 5 | 3 | 3 | Varsha: We need to consider keyword optimization. | The final decision recognized that the task requires strategic selection of skills and keyword optimization to align with recruiters’ searches, so the final effort estimate increased slightly compared to Round 1.
[5 empty] | Hemanth: We should prioritize the most relevant skills. |  |  |  |  | Hemanth: The right skills can enhance discoverability.
[5 empty] | Girish: Let's ensure these skills are in demand. |  |  |  |  | Girish: Prioritizing skills matters for recruiters.
[5 empty] | Wen: This shouldn’t take long. |  |  |  |  | Wen: This will take more thought than expected.
4. Seeking Skill Endorsements | 2 | 3 | 2 | 2 | Varsha: This seems like a straightforward task. | 5 | 5 | 3 | 3 | Varsha: We may need to follow up with some people. | After realizing that the effort required more coordination and follow-ups than initially expected, the team increased the effort score for this task.
[5 empty] | Hemanth: It might involve reaching out to several people. |  |  |  |  | Hemanth: Choosing the right colleagues is essential.
[5 empty] | Girish: I think it's simple to send requests. |  |  |  |  | Girish: Multiple rounds of requests could complicate things.
[5 empty] | Wen: We need to choose who to ask carefully. |  |  |  |  | Wen: It's more effort than I initially thought.
5. Thought Leadership Post | 5 | 8 | 5 | 5 | Varsha: This task seems moderately challenging due to drafting and publishing. | 8 | 8 | 8 | 8 | Varsha: The post needs to be well-researched and engaging. | The final decision recognized that significant effort is needed to write a well-researched, engaging, and optimized article, so the estimate was further increased.
[5 empty] | Hemanth: We need to ensure the post is engaging. |  |  |  |  | Hemanth: Optimizing it for visibility is crucial.
[5 empty] | Girish: It requires thorough research. |  |  |  |  | Girish: We must focus on quality over quantity.
[5 empty] | Wen: This will take time to make it well-structured. |  |  |  |  | Wen: Significant effort is needed for a successful article.
6. Profile Multimedia Enhancements | 3 | 5 | 3 | 3 | Varsha: This should be a simple task of uploading content. | 5 | 5 | 5 | 5 | Varsha: Quality multimedia can enhance the profile. | The effort was increased slightly after recognizing the importance of high-quality multimedia integration and relevance to the profile's purpose.
[5 empty] | Hemanth: We must ensure quality and relevance. |  |  |  |  | Hemanth: We need strategic thought on integration.
[5 empty] | Girish: It's important to integrate multimedia well. |  |  |  |  | Girish: The relevance of multimedia is important.
[5 empty] | Wen: I thought this would be easier than it is. |  |  |  |  | Wen: We must ensure high standards.
7. Professional Networking | 2 | 3 | 2 | 2 | Varsha: Sending connection requests seems straightforward. | 5 | 5 | 5 | 5 | Varsha: We need to focus on the quality of connections. | Personalizing connection requests and targeting the right professionals led to an increased effort estimate for networking on LinkedIn.
[5 empty] | Hemanth: Targeting the right professionals is key. |  |  |  |  | Hemanth: Personalizing requests takes more effort.
[5 empty] | Girish: Personalization is important for effectiveness. |  |  |  |  | Girish: The right strategy will yield better results.
[5 empty] | Wen: It's not as simple as it seems. |  |  |  |  | Wen: Tailoring requests is essential for effective networking.
8. Industry Group Participation | 2 | 3 | 2 | 2 | Varsha: Joining groups seems simple enough. | 5 | 5 | 5 | 5 | Varsha: We need to find the most active groups. | Final decision concluded that the effort to effectively participate in industry groups required ongoing engagement and contribution, leading to a higher effort estimate than initially expected.
[5 empty] | Hemanth: Active participation is key to effectiveness. |  |  |  |  | Hemanth: Ongoing engagement is crucial for networking.
[5 empty] | Girish: We need to contribute meaningfully. |  |  |  |  | Girish: Contributions need to be valuable.
[5 empty] | Wen: I didn't think it would require much effort. |  |  |  |  | Wen: This task requires ongoing effort and commitment.
9. Updating Certifications Section | 3 | 3 | 3 | 3 | Varsha: Adding certifications should be straightforward. | 5 | 5 | 5 | 5 | Varsha: Highlighting certifications correctly is crucial. | The team increased the effort score after recognizing the importance of formatting and highlighting certifications correctly to showcase their relevance.
[5 empty] | Hemanth: We must highlight relevant ones. |  |  |  |  | Hemanth: Selecting the most relevant ones is key.
[5 empty] | Girish: Formatting is key to making them stand out. |  |  |  |  | Girish: We need to ensure proper formatting.
[5 empty] | Wen: It shouldn't take long if we do it right. |  |  |  |  | Wen: This task requires careful consideration of which certifications to include.
10. Track Profile Engagement | 3 | 2 | 2 | 2 | Varsha: Checking analytics seems simple. | 5 | 5 | 3 | 5 | Varsha: Monitoring engagement regularly is key. | The task of monitoring engagement and adjusting
[5 empty] | Hemanth: Adjusting based on data will be necessary. |  |  |  |  | Hemanth: It requires consistent adjustments.
[5 empty] | Girish: It should be straightforward to track engagement. |  |  |  |  | Girish: Interpreting analytics will add to the effort.
[5 empty] | Wen: We need to ensure we make the right adjustments. |  |  |  |  | Wen: Ongoing adjustments based on engagement will take time.